## Job
Job review — estimate versus actual
Yellow cells are yours. Blank means not known: enter 0 for none.
| Estimate | Actual
Price quoted (before any changes) | 12400
Approved changes (added to the price) |  | 900
Materials | 3800 | 4150
Labor hours | 64 | 79
Labor rate per hour | 55 | 55
Subcontractors | 1200 | 1200
Other direct costs | 300 | 410
Supplier credits (reduce materials) |  | 120
What happened
Revenue
Labor cost
Direct cost
Contribution (revenue less direct cost)
Margin (contribution ÷ revenue)
Where it moved (actual less estimate)
Materials, after credits
Labor hours
Labor cost
Subcontractors
Other direct costs
For the next quote
Price that would have kept the planned contribution on these actual costs
Arithmetic on your own numbers — not a market price, and not a prediction of the next job.

## Guide
Job review — how to use it
What it is for: after a job is finished, see where it made or lost money against what you quoted,
and what the price would have needed to be to keep the contribution you planned.
1. On the Job sheet, overwrite the example with one finished job. Only the yellow cells take input.
2. Enter the price you quoted before any changes, and approved changes separately.
3. Enter your estimate and what actually happened, line by line. Hours are hours; money is dollars.
4. Leave a cell blank only if you do not know it. Anything that depends on it will say "unknown".
If there was nothing (no subcontractors, no credit), enter 0.
5. Read "What happened", then "Where it moved", then the price line under "For the next quote".
What it is not: bookkeeping, tax advice, a market price, or a prediction. It does arithmetic on your
numbers and shows its working; the formulas are locked so they cannot be overwritten by accident.
Version 0.1.0. A corrected file gets a new version number; this one is never replaced silently.